## Sheet1
Communication Objective | Activity/Deliverable | Type | Level | Internal/External | Lead | Target Audience(s) | In Which Project Period? | Measure | Target
C.1. Ensure that there is strong and effective communication within and beyond the project partnership | Communication plan | Other (internal plans) | Project | Internal and external | ERYC | All target audiences | 1 | Number of plans | 1
| Interreg NSR project web space | New service | Project | External | ERYC | All target audiences | 1 | Number of sites | 1
| Sullied Sediments Project blog (using Wordpress) | New service | Project | External | UH / ERYC | All target audiences | All | Number of readers | TBC
| Sullied Sediments Twitter feed | New service | Project | External | UH / ERYC | All target audiences | All | Number of followers | TBC
| Use of the Interreg NSR Online Monitoring System | New service | Project | Internal | UH / ERYC | Joint Secretariat | All | N/A | N/A
| Newsletter | Exchange of information event | Project | Internal and external | ERYC | All target audiences | All | Number of issues | 6
| Newsletter | Exchange of information event | Project | Internal and external | ERYC | All target audiences | All | Number of readers | 50
| Individual work package meeting | Exchange of information event | Work package | Internal | Various | Project partnership | All | Number of meetings | 10
| Formal knowledge exchange between work packages | Exchange of information event | Work package | Internal | Various | Project partnership | All | Number of exchanges | 9
C.2. Ensure that the project is delivered effective through the proposed management structure (see Appendix 1) | Advisory Board and Steering Group established | Other (management group) | Project | Internal | UH / ERYC | Project partnership | 1 | Number of groups established | 2
| Steering Group and Project Review meetings | Exchange of information event | Project | Internal | UH / ERYC | Project partnership | All | Number of meetings | 6
| Annual meetings (to include the Advisory Board) | Exchange of information event | Project | Internal | UH / ERYC | Project partnership | 2, 4, 6 | Number of meetings | 3
| Kick-off meeting (for project beneficiaries and advisory partners) | Exchange of information event | Project | Internal | UH / ERYC | Project partnership | 1 | Number of meetings | 1
C.3. Provide partners with appropriate support to ensure they meet our audit and reporting obligations to the Joint Secretariat | General and one-to-one support via skype and email | Exchange of information event | Project | Internal | UH / ERYC | Project partnership | All | Number of online sessions | 7 (min.)
| Spending/delivery plan created for each project beneficiary and work package and an overall project plan | Other (internal plan) | Project | Internal | UH / ERYC | Project partnership | 1 | Number of plans created | 19
| Project period progress and financial report (based on submissions by project beneficiaries) | Report/strategy | Project | Internal | UH / ERYC | Joint Secretariat | 1 | Number of submissions | 6
C.4. Use project communication tools, events and strategic networks to promote the new data toolkits, protocols and guidelines across the NSR and beyond | Society of Environmental Toxicology and Chemistry Conference Workshop (potentially combined with an annual meeting) | Dissemination event | Project | External | UH / ERYC / HAW | Higher education and research Infrastructure/public service provider Interest groups including NGOs Large private enterprise Local, regional and national public authority Sectoral agency | 5 | Number of participants | TBC
| Conference documents | Exchange of information event | Project | External | UH / ERYC / HAW | As above | 5 | Number of information kits | 1
| Publication on the review of pollutant pressures in Europe | Report/strategy | Work package | External | HAW / UH | Higher education and research Infrastructure/public service provider Interest groups including NGOs Local, regional and national public authority Sectoral agency | TBC | Number of readers | 30
| Economic benefits report focused on biological diversity, productivity and hydrology | Report/strategy |  |  |  | As above | TBC | Number of readers | 30
| Government white paper providing monitoring protocol for target WL chemicals | Report/strategy | Work package | External | ESG / UH | As above | TBC | Number of papers | 3
| Publication on legal sediment management frameworks | Report/strategy | Work package | External | OVAM | As above | TBC | Number of readers | 100
| Report on cost-benefit estimations for sediment management decisions | Report/strategy | Work package | External | OVAM | As above | TBC | Number of readers | 25
| Guideline on the evaluation of sediments by application of BEBA/OMEGA | Working practice change | Work package | External | HAW / UH / OVAM / RU | As above | TBC | Number of adopters | TBC
| Training workshop on the BEBA/OMEGA guideline | Exchange of information event | Work package | External | HAW / UH / OVAM / RU | As above | TBC | Number of workshops | 4
| As above | As above | As above | As above | As above | As above | TBC | Number of participants | 40
| Report on higher level eco-toxicological impacts | Report/strategy | Work package | External | RU | As above | TBC | Number of reports | 4
| As above | As above | As above | As above | As above | As above | TBC | Number of readers | 20
C.5. Use the project communication tools to promote the new treatment methods piloted and validated by the project to stakeholders across the NSR and beyond | Conference workshop co-hosted with the NuReDrain project at a water industry event | Dissemination event | Project | External | UH / ERYC | Higher education and research Infrastructure/public service provider Interest groups including NGOs Large private enterprise Local, regional and national public authority Sectoral agency | TBC (5 or 6) | Number of participants | TBC
| Conference documents | Exchange of information event | Project | External | UH / ERYC / Vlakwa | As above | 5 | Number of information kits | 1
| Workshop on the end-of-waste assessment approach for ex situ sediments | Dissemination event | Project | External | OVAM | As above | TBC | Number of participants | 40
C.6. Celebrate the achievements and effectiveness of volunteers participating in the training and field sampling programmes and encourage more people to take community action on local waterways | Citizen geared materials (communications that will convey messages about citizen behaviour and consumer choice affecting the water system) | Exchange of information event | Project | External | UH / ERYC | General public Interest groups including NGOs | 3, 4, 5, 6 | Number of information kits | 1
| App to be used by volunteers to report their sampling findings | New service | Work package | External | UH / ERYC | As above | 3 | Number of users | 80
| Volunteer training programme for sediment sampling | Exchange of information event | Work package | External | UH / ERYC / CRT | As above | 3 | Number of participants | 80
| Coordinated field sampling campaign | Pilots/demonstrations | Work package | External | UH / ERYC / CRT | As above | 3, 4, 5 | Number of roll-outs | 4
| Volunteer behaviour change survey (pre- and post-participation) | Pilots/demonstrations | Work package | External | UH / ERYC | General public (volunteers) | 3, 6 | Number of surveys | 2
C.7. Use joint private-public sector communications to improve awareness about the global need to better understand and manage sediments to protect water resources for future generations | Multi-media communications campaign to promote citizen behaviour change (digital mainly) | Communication initiative | Project | External | UH / ERYC | All target audiences | All | Number of users | 1000