## Blad1
Output indicators voor C5a
| Indicators | Target | Result | Rep 1 | Progress | Rep 2 | Progress | Rep 3 | Progress | Rep 4 | Progress | Rep 5 | Rep 6
| Number of new and/or improved climate change solutions demonstrated | 1 |  | 0 | not due yet | 0 | not due yet | 1 | The C2C approach has been developed and is currently being tested at some project partners (Dordrecht(NL) and VCAB (SWE)). | 0 | The COVID 19 pandemic has resulted in a drastic delay in reaching this objective
| Number of Enterprises participating in cross border , transnational or interregional research projects | 5 |  | 2 | Sayers and Partners and ResilienServices | 1 | US North Carolina Department of Transport | -1 | Owing to a drastic reduction in income, the NCDT has stopped their activities with C5a | 1 | Aveco de Bondt, an engineering company has began participating in interregional research with the Province Drenthe.
| Number of research institutions participating in cross-border transnational or interregional research projects | 10 |  | 1 | Twente University is involved in the project | 1 | Denmarks technical university are a part of the COHERENT project that we have teamed up with. | 1 | The Swedish geotechnical Institute is now onboard | 2 | Dundee University is now on board
| Number of organisations /enterprises adopting new solutions by project end | 35 |  | 0 | anticipated for later |  |  | 1 |  | 4 | Two partners have reported that they expect other organisations will accept the solutions presented by the C2C approach. These are : Municipality of Coevorden Waterboard Vechtstromen Waterboard Drents Overijsselse Delta Ringkøbing-Skjern Municipality
| Number of organizations/ enterprises informed about new solutions by project end | 1000 | 275 | 218 | A majority of the organisations were informed via a keynote speech at the Northsea Conference. Other organisations were involved via the 7UP project network of C5a. Colleagues from the US were informed via the international cooperation projects that are f | 57 | Several of the organisations mentioned below were informed during keynote speeches in England, Denmark and Portugal | 33 | C5a conducted a mid term event in this period. This was comnined with the end event of thr FAIR project. We were thus able to reacht a wide audience group | 93 | 3 partners have conducted workshops whereby many organisations have been informed abou tthis project. Further some partners participated in online webinars and conferences and were therefore able to reach a very large audience .
|  |  | specific organisations per report |  | Aalborg Kommune |  | A1 |  | University of Lund, Sweden
[5 empty] | Aalst |  | Aabenraa |  | Swedish Environmental Protection Agency, Sweden |  | Aalborg Kommune, Limfjordssekretariatet
[5 empty] | Aarhus University |  | Aecom |  |  |  | AAU
[5 empty] | Aberdeen City Council |  | Arup |  | Swedish Geotechnical Institute , Sweden |  | COWI AS
[5 empty] | Aberdeenshire |  | Assens |  | World Maritime University, Sweden |  | Danske Regioner
[5 empty] | Abertay University |  | Association Climatologique de la Moyenne-Garonne et du Sud-Ouest |  | Nordvästra, Sweden |  | DMI
[5 empty] | ACC - The Association of Consultants in Cooperation |  | BAX & COMPANY |  | Skånes vatten och avlopp, Sweden |  | Envidan
[5 empty] | Agence d’Urbanisme et de Développement des Vallées de l’Oise – Oise-les-Vallées (OLV) |  | Bontang City Indonesia |  | Helsingborgs stad, Sweden |  | Femern A/S
[5 empty] | Agroväst Livsmedel AB |  | Chambre d'Agriculture de la Dordogne |  | Lomma kommun, Sweden |  | Frederikshavn Kommune
[5 empty] | Almere |  | Cowi |  | Simrishamns kommun, Sweden |  | Frederikssund Kommune, Plan og Erhverv
[5 empty] | Antwerp City |  | Dansk arkitektforening |  | Båstads kommun, Sweden |  | Geografi studerende ved Københavns Universitet
[5 empty] | Arcadis |  | Dansk kyst- og Naturturisme |  | Trelleborgs kommun, Sweden |  | Geoinfo A/S
[5 empty] | Arla foods |  | Deichacht Esens-Harlingerland |  | Ängelholms kommun, Sweden |  | Geological Survey of Denmark and Greenland (GEUS)
[5 empty] | Arvika teknik AB |  | DHV |  | Höganäs kommun, Sweden |  | GEUS
[5 empty] | atene KOM GmbH |  | Dragør |  | Malmö stad, Sweden |  | Gottlieb Paludan Architects
[5 empty] | Aust Agder |  | HAN University of Applied Sciences |  | Kävlinge kommun, Sweden |  | Grandville
[5 empty] | Berends-Consult |  | Hedensted |  | Vellinge kommun, Sweden |  | Guldborgsund Kommune
[5 empty] | Bergen kommune |  | Higher Council for Scientific Research |  | Landskrona stad, Sweden |  | Haderslev Kommune
[5 empty] | BONUS/BANOS CSA |  | Hjørring |  | Burlövs kommun, Sweden |  | Hasløv & Kjærsgaard
[5 empty] | Bradford City |  | HR Wallingford |  | Skurups kommun, Sweden |  | Hedensted kommune
[5 empty] | Bremen University |  | Hvidovre |  | Ystad kommun, Sweden |  | Helsingør Kommune
[5 empty] | Bremerhaven |  | IDB |  | Kristianstads kommun, Sweden |  | Holstebro Kommune
[5 empty] | Bremische Burgerschaft |  | Instituto Vasco de investigaciones agrarias |  | Bromölla kommun, Sweden |  | Hørsholm Kommune
[5 empty] | Broads Authority |  | JBA |  | Region Skåne, Sweden |  | Insititur for Geovidenskab og naturforvaltning, Københavns Universitet
[5 empty] | Bronderslev kommune |  | København |  | BioConsult SH GmbH & Co. KG, Husum, Germany |  | Karpenhøj Naturcenter
[5 empty] | Bruges |  | Kyst-havnevide |  | BIOCONSULT Schuchardt & Scholle GbR, Bremen, Germany |  | Klimarådgivning
[5 empty] | Bundesanstalt für Geowissenschaften und Rohstoffe |  | Limerick Institute of Technology |  | Federal Waterways Engineering and Research Institute (Bundesanstalt für Wasserbau - BAW), Hamburg,Germany |  | Københavns Professionshøjskole
[5 empty] | Bureau PAU/University of Agder |  | Middelfart |  | Research and Technology Centre West Coast (Forschungs- und Technologiezentrum Westküste FTZ), |  | Kolding Kommune
[5 empty] | Business Region Fyn |  | National Resource Wales |  | Büsum, Germany |  | Kolding Kommune
[5 empty] | Business Region Göteborg |  | Niras |  | Hamburg Port Authority, Hamburg, Germany |  | Lemvig Vand
[5 empty] | Business Vordingborg |  | Orbicon |  | Leibniz University Hannover, Germany |  | Limfjordssekretariatet
[5 empty] | Canal and River Trust |  | Ramboll |  | Schleswig-Holstein Ministry for Energy Transition, Agriculture, Environment, Nature and Digitalization |  | LYCEUM
[5 empty] | Capelle aan den Ijssel City Council |  | Randers |  | Gemeente Rotterdam, The Netherlands |  | MOE A/S
[5 empty] | Cenex Nederland |  | Realdania |  | KWR, The Netherlands |  | Morsø Kommune
[5 empty] | Center for e-health at University of Agder |  | Region Midt |  | NAIAD project |  | NIRAS
[5 empty] | Centexbel |  | Resiliense |  |  |  | Norddjurs Kommune
[5 empty] | Ciria |  | Ringkøbing Skjern |  |  |  | Nordiq Group
[5 empty] | City of Mechelen |  | RWS |  |  |  | Odder Kommune
[5 empty] | City of Oldenburg |  | Sheffield AC |  |  |  | Odense Kommune
[5 empty] | City of Roeselare |  | Sielacht Dornum |  |  |  | Rambøll
[5 empty] | City of Turnhout |  | Sielacht Esens |  |  |  | Randers kommune
[5 empty] | Common Wadden Sea secretariat |  | Somerset Rivers Authority Project Manager Co-adapt |  |  |  | Region Hovedstaden
[5 empty] | Dachverband Feldberegnung Uelzen |  | Sweco |  |  |  | Region Midtjylland
[5 empty] | De Vlaamse waterweg NV |  | TEAM (Jacobs) |  |  |  | Region Syddanmark
[5 empty] | Delta Alliance |  | Team2100 |  |  |  | Ringkøbing-Skjern Kommune
[5 empty] | Deltares |  | Univ. Aalborg |  |  |  | Samn Forsyning
[5 empty] | Deutscher Verband für Landschaftpflege |  | Univ. Copenhagen |  |  |  | Schønherr
[5 empty] | Diakonisches Werk Bremen |  | Univ. Delft |  |  |  | Seden Strandby Grundejerforening
[5 empty] | Dordrecht City Council |  | Univ. Lund |  |  |  | Skive Kommune
[5 empty] | Durham University |  | Univ. Twente |  |  |  | Smith Innovation
[5 empty] | Dutch Marine Energy Centre |  | Univ. Utrecht |  |  |  | Stevns Kommune
[5 empty] | East of Scotland European Consortium (ESEC) |  | Universidade de Aveiro |  |  |  | Struer Kommune
[5 empty] | East Riding of Yorkshire Council |  | Universidade de Coimbra |  |  |  | Svineholm Digelag (DNNK)
[5 empty] | Eastern Norway County network |  | Universidade de Trás-os-Monte e Alto Douro |  |  |  | SWECO Danmark A/S
[5 empty] | ECOSHAPE |  | University of Exeter |  |  |  | Syddjurs Kommune
[5 empty] | EFEC |  | Vejle |  |  |  | Teknologiens Mediehus/Ingeniøren
[5 empty] | Enfield council |  | Westcountry Rivers Trust |  |  |  | Teknologirådet
[5 empty] | Enschede City Council | [5 empty] | Thisted Kommune
[5 empty] | Environment Agency | [5 empty] | UCL Erhvervsakademi og Professionshøjskole
[5 empty] | ERAC B.V. | [5 empty] | Vandvender
[5 empty] | Erasmus University Rotterdam | [5 empty] | VIA University College
[5 empty] | Essex & Suffolk Rivers Trust | [5 empty] | WSP
[5 empty] | Essex County Council | [5 empty] | Wulfsberg.dk
[5 empty] | Eureka Consult | [5 empty] | YWPDK
[5 empty] | European and Regional Affairs Consultants | [5 empty] | Brighton & Hove City Council (UK, Local authority)
[5 empty] | European Institue for Innovation | [5 empty] | Environment Agency (UK, Sectoral agency)
[5 empty] | European Policy Solutions | [5 empty] | Farys (BE, Drinking water company)
[5 empty] | Flemish Ministry of Mobility and Public Works | [5 empty] | Flanders Agency for Nature & Forestry (BE, Sectoral agency)
[5 empty] | Gemba Seafood Consulting | [5 empty] | Flanders Coastal Agency (BE, Regional authority)
[5 empty] | Gemeente Emmen | [5 empty] | Flanders Insitute for the Sea (BE, Regional authority)
[5 empty] | Gent city Council | [5 empty] | Flanders Land Agency (BE, Sectoral agency)
[5 empty] | Global Centre for Adaptation | [5 empty] | Flemish Government (BE, Regional government)
[5 empty] | Göteborgs Stad | [5 empty] | Gemeente Middelburg (NL, Local authority)
[5 empty] | Göteborgs Universitet | [5 empty] | Ghent University (BE, University)
[5 empty] | Grenspark Kalmthoutse heide | [5 empty] | Kent Downs (UK, Ngo)
[5 empty] | Groningen City Club | [5 empty] | OOWV (DE, Sectoral agency)
[5 empty] | Groningen University | [5 empty] | Province of West-Flanders (BE, Regional authority)
[5 empty] | Hamburg | [5 empty] | Stad Oostende (BE, Local authority)
[5 empty] | Hamburg Institute of International Economics (HWWI) | [5 empty] | University of Dundee (UK, University)
[5 empty] | Helsingborg | [5 empty] | Waterschap Scheldestromen (NL, Sectoral agency)
[5 empty] | Herning kommune | [5 empty] | Gemeente Coevorden
[5 empty] | Hogeschool Zeeland | [5 empty] | Waterschap Vechtstromen
[5 empty] | Hordaland | [5 empty] | Provincie Overijssel
[5 empty] | Horsens kommune | [5 empty] | Waterschap Drents Overijsselse Delta
[5 empty] | Howest | [5 empty] | Aveco de Bondt
[5 empty] | HyER | [5 empty] | IABR
[5 empty] | HyTrEc2 project | [5 empty] | PZH
[5 empty] | Interessen Im Fluss | [5 empty] | ProRail
[5 empty] | IUCN | [5 empty] | Stedin
[5 empty] | Jade Hochschule | [5 empty] | Evides
[5 empty] | Jammerbugt Kommune | [5 empty] | HKV
[5 empty] | Kent County Council | [5 empty] | Veiligheidsregio
[5 empty] | KIMO | [5 empty] | City Council of Enschede
[5 empty] | Kystdirektoratet | [5 empty] | Vrije University Brussels
[5 empty] | Land Niedersachsen, ArL WE | [5 empty] | Université libre de Bruxelles
Landesamt für Bergbau, Energie und Geologie Niedersachsen
Landesamt für Landwirtschaft, Umwelt und ländliche Räume Schleswig-Holstein
Landesbetrieb für Kusten un Naturschutz Schlesswig-Holstein
Landkreis Diepholz
Landwirtschaftskammer Niedersachsen
Länsstyrelsen Skane
Länsstyrelsen Värmland
Leibniz-Institut für Angewandte Geophysik
Leiedal
Lower Saxon Ministry for Federal and European Affairs and Regional Development
LSGB
Maritieme Academie Harlingen
Maritieme Dienstverlening en Kust
Mechelen
MHCLG
Møre og Romsdal fylkeskommune
Morsø Municipality
National Flood Forum
Nationale Geologiske Undersøgelser for Danmark og Grønland
Naturdirektoratet
Natuurpark
New Energy Coalition
Niedersächsischer Landesbetrieb für Wasser- Küsten und Naturschutz NLWKN
Nordic Baltic Wetland Group
Norfolk County Council
Norfolk Rivers Trust
Norges Vassdragts og Energidirektoratet
North Carolina Coastal Department
North Carolina Department of Transport
North Carolina University
Northern Institute of Thinking
Northumbrian Water Limited
Oldenburgisch-Ostfriesischer Wasserverband
OOWV
Oppland fylekskommune
Ostfold fylkeskommune
Pindstrup
Province of Antwerp
Province of Drenthe
Province of Flevoland
Province of Fryslan
Province of Groningen
Province of Noord-Holland
Province of Overijssel
Province of Zuid Holland
Provincie Oost Vlaanderen
Provincie West-Vlaanderen
Reeleaf BV
Reframe
Region Halland
Region Hannover
Region Kristiansand
Region Midtjylland
Region Nordjylland
Region Örebro
Region Syddanmark
Regionaal landschap De Voorkempen
Regional Water Authority Hollands Noorderkwartier
Regional Water Authority Hunze en Aa's
Regional Water Authority Noorderzijlvest
Regional Water Authority Schieland and Krimpenerwaard
Regional Water Authority Vechtstromen
Rijkswaterstaat
Robert Gordon University
Rotterdam
Royal College of Art
Royal Haskoning DHV
RUN
RVO
Sayers and Partners
Schouwen Duiveland Council
Scottish Environment Protection Agency
Scottish Government
Scottish Natural Heritage
Sheffield University
Skagen Uddannelsescenter
Smagen af Danmark (Taste of Denmark)
Sogn og Fjordane fylkeskommune
Solutionweb ApS
South Norway European Office
Southend on Sea Borough Council
Ständige Vertretung der Bundesrepublik Deutchland bei der EU
Stavanger region
Stiftung Naturschutz
Svinesundskommittén
Sweden Water Research / WIN Water
Swedish Agency for Economic and Regional Growth
Syndicat Mixte baie de Somme - Grand Littoral Picard
Telemark
Terra Nordica
The Rivers Trust
Tillväxtverkety
Trøndelag County Council
TUHH Institute of River and Coastal Engineering
Turnhout
Tweed Forum
Twente University
UNESCO IHE
University of Dundee
University of Glasgow
University of Hull
University of Oldenburg
US Army Corps of Engineers
US FHWA
Van Hall Larenstein
VanOs
Västra Götaland
Vejle kommune
Vest Agder
Vestfold
VGR
Videum AB
VIVES University College
Vlaamse Milieumaatschappij
VLAIO
Vordingborg Port
Washington State Department of Transport
Water Alliance
waterschap Vechtstromen
Wear Rivers Trust
Westerkwartier Council
Wetlands International