## WP deliverables
WP | Deliverable | Indicator | Explanation | Target | Report 1 | Report 2 | Report 3 | Report 4 | Report 5 | Report 6 | Report 7 | Total | Description/evidence
Management | 1 Coordination Group (CGM), Steering Group (SG) and Consultative Group (CG) meetings | Exchange of Information Event (Internal) | CGM 6x, SG 3x and CG 3x meetings (project management and monitoring) | 12 | 3 | 1 | 2 | 2 | 1 | 2 | 2 | 13 | CGM: 7-02-2019 (Brussels), 19/21-06-2019 (Ringkobing), 6/8-11-2019 (Essens), 5-6-2020 (online), 6-11-2020 (online), 2-06-2021 (online), 21/22-10-2021 (hybrid Dordrecht), March 2022 (Denmark), May 2022 (end event) SG: 8-02-2019, 17-6-2020, 14-11-2021 Consultative Group: 21-10-2020
Management | 1 Coordination Group meetings (sub) | Number of participants | Number of participants: 12 meetings of 10 Partner organisations results in 120 participants | 120 | 30 | 10 | 20 | 17 | 10 | 20 | 20 | 127 | Report 1: 2 CGMs, all partners (10) participated + 1 SG meeting all partners participated Report 4: 1x all partners CGM + CG 7 projects
Management | 2 Action plan, risk log, reports and Mid term review | Report / Stragegy | The action plan, risk log, normal reporting and mid term reviews are seen as means to make sure the project is in line with the expected production and funding plan. These reports will be shared with the CGM and SG in their meetings. | 9 | 2 | 1 | 1 | 1 | 2 | 1 | 2 | 10 | Report 1: Action plan with included risk log Report 2: report 1 filed Report 3: report 2 filed Report 4: report 3 filed Report 5: report 4 filed + action plan Report 6: report 5 filed Report 7: report 6 filed + report 7
Management | 2 Action plan, risk log, reports and Mid term review (sub) | Number of readers | The different reports will be read by the project members, i.e. the CGM members and the SG members | 180 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 140
Management | 3 Partnership agreement and subsidy contract | Other |  | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | Partnership Agreement and Subsidy Contract Report 6: following major change new subsidy contract was signed.
Communication | 1 Plan for operational and strategic communication activities, including separate plans per region | Report / Stragegy | A living document on communication will be prepared and regularly updated. the regions will translate the overall strategy in their own, region specific plans. 1 overall and 10 individual plans makes 11 plans | 11 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 3 | Report 2: overall communication strategy + communication plan Varmland Report 3: communication plan Drenthe
Communication | Plan for operational and strategic communication activities (sub) | Number of readers | The CGM members and the communication officers will read this document, making 10 partner organisations times 2 persons is 20 persons | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 20
Communication | 2 Start, Midterm and End events | Exchange of Information Event (Internal) | 3 events will be organised, 1 at the start, one halfway and 1 at the end of the project | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 3 | Start event in Brussels 6/7-02-2019 Mid term event 4-6-2020 End event May 2022
Communication | Start, Midterm and End events (sub) | Number of participants | Start event will probably entail the partners: 10 Mid term and End event will entail approximately 100 visitors each | 210 | 26 | 0 | 223 | 0 | 0 | 0 | 45 | 294 | Mid term event online
Communication | 3 The Story about C5A | Communication initiative | “The story about C5A” will, apart from being a story, also be transformed into an explanatory graphic and a short video, for enhanced visual impact of the project aims, objectives and results. We'll also have other communication activities. 3 +50=53 | 53 | 6 | 3 | 6 | 10 | 7 | 2 | 19 | 53 | Report 1: 5 news articles on the website + 1 video Report 2: 3 news articles on the website Report 3: 5 news articles on the website + 1 video Report 4: 9 news articles on the website + 1 video Report 5: 7 news articles on the website Report 6: 1 news article on the website + 1 exhibition Report 7: 3 news articles on the website + 11 videos on the interactive website + 5 posts on LinkedIn and FB
Communication | The Story about C5A | Number of users | The Story, its explanographic and movie will be widely distributed. The number of readers of the Story is estimated to be 100, the numbers of viewees of the movie and the explanographic is estimated at 1000 each. Other initiatives: 500 views/year. | 3600 | 187 | 50 | 43 | 432 | 528 | 167 | 1585 | 2992 | Report 1: Video 87 views, views website 100 Report 2: estimation of views website 50 Report 3: within partnership 43 Report 4: views on the website Report 5: views website 416, views video Drenthe 112 Report 6: views youtube Cloud2Coast 159, additional views video Drenthe 8 Report 7: 565 views website, 1000 views social media, Drenthe video 20 views
Communication | 4 Digital exposure and online exchange of information | Other | This section covers the digital tools for internal and external communication. There will be one genera website, 10 individual websites and 1 online tool, making 12. Also, we will use social media for small articles, images and video. | 12 | 3 | 0 | 1 | 0 | 8 | 0 | 0 | 12 | Report 1: general website on Interreg, trello website for internal communication, Värmland website Report 3: video on RWS website Report 5: check all other partners have also mentioned C5a on their website
WP3 Co-creation of the C2C approach | 1 Exploring existing adaptation approaches and barriers to Cloud-to-Coast | Report / Stragegy | This analysis draws the landscape on which the C2C approach will be based during its development | 1 | 0 | 0 | 1 |  |  |  |  | 1 | Report 3: Patchways to resilient spatial planning in flood risk management (Barriers and opportunities for flood resilient spatial planning)
WP3 Co-creation of the C2C approach | Exploring existing adaptation approaches and barriers to Cloud-to-Coast (sub) | Number of readers | Report will be read by our partners (10), the PLG (10), CG (7) and the participants of the cases (approximately 10 per case = 70) | 97 | 0 |  | 27 |  | 30 | 20 | 15 | 92 | Report 3: when the document was written it was distributed to the members of the CGM, SG and CG. Report 5: the document was distributed to the workshops of the 3 case studies. Report 6: the document was distributed to the workshops of the 2 case studies. Report 7: document distributed to the ambassadors and water managers within VMM.
WP3 Co-creation of the C2C approach | 2 Developing a conceptual model of the Cloud-to-Coast approach | New services | This model will be the starting point for testing the approach. | 1 |  |  | 1 | 0 | 0 | 0 |  | 1 | Report 3: concept note
WP3 Co-creation of the C2C approach | Developing a conceptual model of the Cloud-to-Coast approach (sub) | Number of users | This will be used by persons in the 7 case studies. approximately 10 external per case, makes 70. And of course the partners, 10. Makes 80 together. | 80 | 0 |  | 10 |  | 30 | 20 | 20 | 80 | Report 3: the concept note was read by the partners. Report 5: the concept note was distributed to the workshop participants of the 3 case studies. Report 6: the concept note was distributed to the workshop participants of 2 further case studies. Report 7: the concept note was distrubuted to the workshop participants of the 2 last case studies.
WP3 Co-creation of the C2C approach | 3 Evaluation and adjustment of the C2C approach | Working practice change | The adjustments to the models as a result of the feedback and experiences of the case studies will lead to an improved model that is ready for broader uptake. | 1 | 0 | [5 empty] | 1 | 1
WP3 Co-creation of the C2C approach | 4 Internal working group meetings | Exchange of Information Event (Internal) | The partners will meet regularly. Physically if needed, yet digitally if possible to minimize the projects foot print. Group will meet at least bimonthly in any kind of form. 3 years times 6 makes 18 meetings. | 18 | 3 | 8 | 8 | 6 | 6 | 3 | 2 | 36 | Report 1: online meetings 24-02-2019, 28-05-2019, 11-06-2019 Report 2: science team meets every 4 weeks Report 3: science team had 3 online meetings in this period Report 4: meets every 4 weeks Report 5: meets once every 4 weeks Report 5: meets once every 4 weeks
WP3 Co-creation of the C2C approach | Internal working group meetings (sub) | Number of participants | WP3 involves all partners, yet, not al will be at each meeting, especially not during the development phase. An estimated average of 5 persons will cover the attendees. 18 times 5 is 90 participants. | 90 | 9 | 24 | 24 | 18 | 18 | 9 | 6 | 108 | Report 1: partners RWS, UT, Sayers present at 3 meetings.
WP4 Application of the Cloud to Coast Approach in Practice | 1 Common understanding, cross comparisons and a guidance for authorities and policy makers | Report / Stragegy | A cross-comparison of the existing will result in the identification of issues and enablers for C2C. From this a roadmap will be made that guides authorities and practitioners in designing and implementing their future climate adaptation pathways | 3 | 0 | 1 |  |  | 1 | 0 | 1 | 3 | Report 2: survey held Report 5: supporting tools overview & strategic planning for flood resilience: four prerequisites
WP4 Application of the Cloud to Coast Approach in Practice | Common understanding, cross comparisons and a guidance for authorities and policy makers (sub) | Number of readers | The common understanding and cross comparison docs will be read by the partners (10), the CG (7) and PLG (10), making 2x27=54. The guidance will be read by all indirect project partners from the 7 projects (100) and networking partners (approx 20) | 174 | 0 | 17 |  |  | 17 | 20 | 45 | 99 | Report 3: the survey was read by members of the CGM and CG. Report 5: the document was read by members of the CGM and CG. Report 6: both documents were presented to the Ambassador group.
WP4 Application of the Cloud to Coast Approach in Practice | 2 Workshop for analysis and reflection and regular internal meetings | Exchange of Information Event (Internal) | C5A partner workshop, outcomes will be covered in a report. Regular meetings (6, physical if not digitally possible) will be on preparing and coordinating the implementation of the Work Package and liaising with WP 3 and 5 about inter linkages. | 7 | 1 | 1 | 2 | 2 | 1 | 1 | 3 | 11 | Report 1: workshop during CGM Ringkobing June 2019 Report 2: workshop during CGM Essens November 2019 Report 3: 2 workshops for case study leads Report 4: 1 reflection and 1 outlook workshop for case study leads Report 5: 1 peer-2-peer workshop Report 6: 1 peer-2-peer workshop Report 7: 2 reflection workshops and 1 peer-2-peer workshop
WP4 Application of the Cloud to Coast Approach in Practice | Workshop for analysis and reflection (sub) | Number of participants | partners | 10 | 10 | [6 empty] | 10 | All partners participated
WP4 Application of the Cloud to Coast Approach in Practice | 3 C5A Case Studies | Pilots / demonstrations | At least one workshop per case study will be held on site. | 7 | 0 | 0 | 2 | 5 | 2 | 1 | 2 | 12 | Report 3: case study workshop at RWS and Varmland Report 4: case study workshop Drenthe, RWS, Varmland (2), VMM Report 5: case study workshop Kent, RWS Report 6: case study workshop VMM Report 7: case study workshop NLWKN and DCA
WP5 Policy learning on the Cloud-to-Coast Approach | 1 Policy Learning Group meetings and internal meetings | Exchange of Information Event (Internal) | PLG will meet 3 times Internal meetings back to back with coordination group meetings 6 times | 9 | 2 | 1 | 1 | 2 | 2 | 2 | 0 | 10 | Report 1: internal meeting 7-2-2019, 19-06-2019 Report 2: internal meeting 8-11-2019 Report 3: internal meeting 5-6-2020 Report 4: internal meeting 6-11-2020, Ambassadors meeting 2-12-2020 Report 5: internal meeting 2-6-2021, Ambassadors meeting 29-6-2021 Report 6: internal meeting 21-10-2021, Ambassadors meeting 23-11-2021
WP5 Policy learning on the Cloud-to-Coast Approach | Policy Learning Group meetings and internal meetings (sub) | Number of participants | PLG meetings consist of 10 attendees. Internal meetings of approximately 5. 3x10+6x5=60 attendees | 60 | 10 | 5 | 10 | 21 | 24 | 18 | 0 | 88 | Report 1: 2 meetings x 5 participants Report 2: 1 meeting x 5 participants Report 3: 1 meeting all partners participated Report 4: internal meeting all partners, Ambassadors meeting 11 participants Report 5: internal meeting all partners, Ambassadors meeting 14 participants Report 6: internal meeting all partners, Ambassadors meeting 8 participants.
WP5 Policy learning on the Cloud-to-Coast Approach | 2 The C5A Brussels workshops | Exchange of Information Event (Internal) | A meeting with several policy stakeholders and influencers will be held at the start and end of the project. | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Report 1: at the kick-off meeting in Brussels
WP5 Policy learning on the Cloud-to-Coast Approach | The C5A Brussels workshops (sub) | Number of participants | We will invite representatives of DG's Regio, ENV, CLIMA and the North Sea Commission , as well as MEPs and top influencers on the climate change field. We aim at 2 times 10 participants. | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | Report 7: 3 ambassadors involved in panel discussions at the end event.
WP5 Policy learning on the Cloud-to-Coast Approach | 3 White paper on Cloud to Coast approach | Report / Stragegy | This white paper will be sent to local, regional, national and EU representatives | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | Report 7: white paper published
WP5 Policy learning on the Cloud-to-Coast Approach | White paper on Cloud to Coast approach (sub) | Number of readers | We aim at the white paper reaching the decision makers desks of all 100 partners in the 7 projects, those of the DGs ENV, CLIMA and REGIO, the North Sea Commission (5), MEPs (5). | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | Report 7: distributed to partners and ambassadors.
26

## Output-solutions demonstrated
Solutions demonstrated | Report
C-2-C approach is demonstrated in all case studies | 3
Kent Future Explorer charts | 6
Holistic roadmap for flood risk management Denmark | 7

## Output-enterprises participatin
Enterprise | Report
Paul Sayers | 1
ResilienServices | 1
Aveco de Bondt | 4
Witteveen & Bos | 7
Farmers advisory | 7
Danish society of dyraulic engineers | 7

## Output-research inst participat
Research institutes | Report
University of Twente | 1
Technical University Denmark | 2
Swedish Geotechnical Institute | 3
Dundee University | 4
Via University College | 7
Aarhus University | 7
Copenhagen University | 7
Karlstad University | 7

## Output-adopting solutions
Organisations | Report
Municipality of Coevorden | 4
Waterboard Vechtstromen | 4
Waterboard Drents Overijsselse Delta | 4
Ringkøbing-Skjern Municipality | 4
NLWKN Betriebsstelle Norden | 6
18 Danish municipaliteis | 7
KCC | 7
Kystdirektoratet | 7
VMM | 7
UT | 7
Provincie Overijssel | 7
Provincie Drenthe | 7
Sayers | 7
Varmland | 7
Region Midtjylland | 7
18 participants in workshops Varmland | 7
Within the workshop of the province of Drenthe, municipality Coevorden and waterboards Vechstromen and Drents Overijsselse Delta agreed on keeping the flood plain Coevorden as a spatial reservation and will continue to apply the C2C approach on the Vecht.
Ringkøbing-Skjern Municipality will adopt the C2C approach in a process plan.
NLWKN Norden will adopt the C2C approach.

## Output-informed
Organisation | Report
€ureka Consult | 1
A1 | 2
Aabenraa | 2
Aalborg Kommune | 1
Aalst | 1
Aarhus University | 1
AAU | 4
Aberdeen City Council | 1
Aberdeenshire | 1
Aberdeenshire Youth Council Representative - Aberdeenshire Council | 1
Abertay University | 1
ACC - The Association of Consultants in Cooperation | 1
Aecom | 2
Agence d’Urbanisme et de Développement des Vallées de l’Oise – Oise-les-Vallées (OLV) | 1
Agroväst Livsmedel AB | 1
Almere | 1
Amt für regionale Landesentwicklung Weser-Ems - Domänenverwaltung | 6
Ängelholms kommun, Sweden | 3
Antwerp City | 1
Arcadis | 1
Arla foods | 1
Arup | 2
Arvika teknik AB | 1
Assens | 2
Association Climatologique de la Moyenne-Garonne et du Sud-Ouest | 2
atene KOM GmbH | 1
Aust Agder | 1
Aveco de Bondt | 4
Basque Centre for Climate Change, | 6
Båstads kommun, Sweden | 3
BAX & COMPANY | 2
Berends-Consult | 1
Bergen kommune | 1
BIOCONSULT Schuchardt & Scholle GbR, Bremen, Germany | 3
BioConsult SH GmbH & Co. KG, Husum, Germany | 3
Bontang City Indonesia | 2
BONUS/BANOS CSA | 1
Bradford City | 1
Bremen University | 1
Bremerhaven | 1
Bremische Burgerschaft | 1
Brighton & Hove City Council (UK, Local authority) | 4
Broads Authority | 1
Bromölla kommun, Sweden | 3
Bronderslev kommune | 1
Bruges | 1
Bundesanstalt für Geowissenschaften und Rohstoffe | 1
Bureau PAU/University of Agder | 1
Burlövs kommun, Sweden | 3
Business Region Fyn | 1
Business Region Göteborg | 1
Business Vordingborg | 1
Büsum, Germany | 3
Canal and River Trust | 1
Capelle aan den Ijssel City Council | 1
Cenex Nederland | 1
Center for e-health at University of Agder | 1
Centexbel | 1
Chalmers/Renova _ Sweden | 5
Chambre d'Agriculture de la Dordogne | 2
Ciria | 1
City of Mechelen | 1
City of Oldenburg | 1
City of Roeselare | 1
City of Turnhout | 1
Common Wadden Sea secretariat | 1
Cowi | 2
COWI AS | 4
Dachverband Feldberegnung Uelzen | 1
Dansk arkitektforening | 2
Dansk kyst- og Naturturisme | 2
Danske Regioner | 4
De Vlaamse waterweg NV | 1
De Vlaamse Waterweg nv - Belgium | 5
Deichacht Esens-Harlingerland | 2
Delta Alliance | 1
Deltares | 1
Department for Public Health (South Holland) - Netherland | 5
Department of Mobility and Public Works - Belgium | 5
Deutscher Verband für Landschaftpflege | 1
DHV | 2
Diakonisches Werk Bremen | 1
DMI | 4
Dordrecht City Council | 1
Dragør | 2
Durham University | 1
Dutch Marine Energy Centre | 1
East of Scotland European Consortium (ESEC) | 1
East Riding of Yorkshire Council | 1
Eastern Norway County network | 1
ECOSHAPE | 1
EFEC | 1
EGM Architects - Netherland | 5
Energiforsk (research and knowledge institute in energy research) | 2
Enfield council | 1
Enköping municipality | 4
Envidan | 4
Environment Agency | 1
Erasmus University Rotterdam | 1
Eskilstuna municipality | 4
Essex & Suffolk Rivers Trust | 1
Essex County Council | 1
European and Regional Affairs Consultants | 1
European Institue for Innovation | 1
European Policy Solutions | 1
Evides | 4
Farys (BE, Drinking water company) | 4
Fastighetsägarna | 3
Federal Waterways Engineering and Research Institute (Bundesanstalt für Wasserbau - BAW), Hamburg,Germany | 3
Femern A/S | 4
Fjordgruppen – Denmark | 5
Flanders Agency for Nature & Forestry (BE, Sectoral agency) | 4
Flanders Coastal Agency (BE, Regional authority) | 4
Flanders Hydraulics Research (DMOW) – Belgium | 5
Flanders Insitute for the Sea (BE, Regional authority) | 4
Flanders Land Agency (BE, Sectoral agency) | 4
Flemish Government (BE, Regional government) | 4
Flemish Ministry of Mobility and Public Works | 1
Forshaga municipality | 3
Fortum (hydropower owner in Klarälven) | 2
Frederikshavn Kommune | 4
Frederikssund Kommune, Plan og Erhverv | 4
Freie Universitat Berlin, | 6
Fylkesmannen Innlandet | 3
Gemba Seafood Consulting | 1
Gemeente Coevorden | 4
Gemeente Emmen | 1
Gemeente Enschede | 1
Gemeente Middelburg (NL, Local authority) | 4
Gemeente Rotterdam, The Netherlands | 3
Gent city Council | 1
Geografi studerende ved Københavns Universitet | 4
Geoinfo A/S | 4
Geological Survey of Denmark and Greenland (GEUS) | 4
Ghent University (BE, University) | 4
Global Centre for Adaptation | 1
Göteborgs Stad | 1
Göteborgs Universitet | 1
Gottlieb Paludan Architects | 4
Grandville | 4
Grenspark Kalmthoutse heide | 1
Groningen City Club | 1
Groningen University | 1
Guldborgsund Kommune | 4
Håbo municipality | 4
Haderslev Kommune | 4
Hagfors municipality | 3
Hamburg | 1
Hamburg Institute of International Economics (HWWI) | 1
Hamburg Port Authority, Hamburg, Germany | 3
Hammarö municipality | 3
HAN University of Applied Sciences | 2
Hasløv & Kjærsgaard | 4
Hedensted | 2
Helmholtz Centre of Environment Research | 6
Helsingborg | 1
Helsingør Kommune | 4
Herning kommune | 1
Higher Council for Scientific Research | 2
Hjørring | 2
HKV consultants- Netherland | 4
Höganäs kommun, Sweden | 3
Hogeschool Zeeland | 1
Holbaek Municipality - Denmark | 5
Holstebro Kommune | 4
Hordaland | 1
Horsens kommune | 1
Hørsholm Kommune | 4
Howest | 1
HR Wallingford | 2
Hvidovre | 2
HyER | 1
HyTrEc2 project | 1
IABR | 4
IDB | 2
Insititur for Geovidenskab og naturforvaltning, Københavns Universitet | 4
Instituto Vasco de investigaciones agrarias | 2
Interessen Im Fluss | 1
IUCN | 1
Jade Hochschule | 1
Jammerbugt Kommune | 1
JBA | 2
Karlstad municipality | 3
Karlstad university | 3
Karpenhøj Naturcenter | 4
Kaunas University of Technology, | 6
Kävlinge kommun, Sweden | 3
Kent Downs (UK, Ngo) | 4
Kent Wildlife Trust - UK | 5
Kentish Stour Countryside Partnership - UK | 5
Kil municipality | 3
KIMO | 1
Klimarådgivning | 4
København | 2
Københavns Professionshøjskole | 4
Kolding Kommune | 4
Köping municipality | 4
Kristianstads kommun, Sweden | 3
KWR, The Netherlands | 3
Kyst-havnevide | 2
Land Niedersachsen, ArL WE | 1
Landesamt für Bergbau, Energie und Geologie Niedersachsen | 1
Landesamt für Landwirtschaft, Umwelt und ländliche Räume Schleswig-Holstein | 1
Landesbetrieb für Kusten un Naturschutz Schlesswig-Holstein | 1
Landkreis Diepholz | 1
Landkreis Wittmund | 6
Landskrona stad, Sweden | 3
Landwirtschaftskammer Niedersachsen | 1
Länsstyrelsen Skane | 1
Länsstyrelsen Värmland | 1
Länsstyrelsen i Blekinge län | 3
Länsstyrelsen i Dalarnas län | 3
Länsstyrelsen i Gävleborgs län | 3
Länsstyrelsen i Gotlands län | 3
Länsstyrelsen i Hallands län | 3
Länsstyrelsen i Jämtlands län | 3
Länsstyrelsen i Jönköpings län | 3
Länsstyrelsen i Kalmar län | 3
Länsstyrelsen i Kronobergs län | 3
Länsstyrelsen i Norrbottens län | 3
Länsstyrelsen i Örebro län | 3
Länsstyrelsen i Östergötlands län | 3
Länsstyrelsen i Skåne län | 3
Länsstyrelsen i Södermanlands län | 3
Länsstyrelsen i Stockholms län | 3
Länsstyrelsen i Uppsala län | 3
Länsstyrelsen i Värmlands län | 3
Länsstyrelsen i Västerbottens län | 3
Länsstyrelsen i Västernorrlands län | 3
Länsstyrelsen i Västmanlands län | 3
Länsstyrelsen i Västra Götalands län | 3
Leibniz University Hannover, Germany | 3
Leibniz-Institut für Angewandte Geophysik | 1
Leiden University | 6
Leiedal | 1
Lemvig Vand | 4
Limerick Institute of Technology | 2
Limfjordssekretariatet | 4
Lomma kommun, Sweden | 3
Lower Saxon Ministry for Federal and European Affairs and Regional Development | 1
LRF | 3
LSGB | 1
LYCEUM | 4
Malmö stad, Sweden | 3
Malung-Sälen municipality | 3
Maritieme Academie Harlingen | 1
Maritieme Dienstverlening en Kust | 1
Mechelen | 1
MHCLG | 1
Middelfart | 2
MOE A/S | 4
Møre og Romsdal fylkeskommune | 1
Morsø Municipality | 1
Munkfors municipality | 3
NAIAD project | 3
National Flood Forum | 1
National Resource Wales | 2
Nationale Geologiske Undersøgelser for Danmark og Grønland | 1
Nationalparkverwaltung Niedersächsisches Wattenmeer | 6
Natural England -UK | 5
Naturdirektoratet | 1
Natuurpark | 1
New Energy Coalition | 1
Niedersächsischer Landesbetrieb für Wasser- Küsten und Naturschutz NLWKN | 1
Niras | 2
NIRAS | 4
Norddjurs Kommune | 4
Nordic Baltic Wetland Group | 1
Nordiq Group | 4
Nordvästra, Sweden | 3
Norfolk County Council | 1
Norfolk Rivers Trust | 1
Norges Vassdragts og Energidirektoratet | 1
North Carolina Coastal Department | 1
North Carolina Department of Transport | 1
North Carolina University | 1
Northern Institute of Thinking | 1
Northumbrian Water Limited | 1
NVO | 3
Odder Kommune | 4
Odense Kommune | 4
Oldenburgisch-Ostfriesischer Wasserverband | 1
OOWV | 1
Oppland fylekskommune | 1
Orbicon | 2
Ostfold fylkeskommune | 1
Pindstrup | 1
Port Of Antwerp - Belgium | 5
Profu | 3
ProRail | 4
Province of Antwerp | 1
Province of Flevoland | 1
Province of Fryslan | 1
Province of Groningen | 1
Province of Noord-Holland | 1
Province of Overijssel | 1
Province of Zuid Holland | 1
Provincie Oost Vlaanderen | 1
Provincie West-Vlaanderen | 1
Räddningstjänsten Hagfors kommun | 3
Räddningstjänsten Karlstadregionen | 3
Räddningstjänsten Sunne/Torsby | 3
Ramboll | 2
Randers kommune | 2
Realdania | 2
Reeleaf BV | 1
Reframe | 1
Region Halland | 1
Region Hannover | 1
Region Hovedstaden | 4
Region Kristiansand | 1
Region Midt | 2
Region Nordjylland | 1
Region Örebro | 1
Region Skåne, Sweden | 3
Region Syddanmark | 1
Regionaal landschap De Voorkempen | 1
Regional Water Authority Hollands Noorderkwartier | 1
Regional Water Authority Hunze en Aa's | 1
Regional Water Authority Noorderzijlvest | 1
Regional Water Authority Schieland and Krimpenerwaard | 1
Regional Water Authority Vechtstromen | 1
Research and Technology Centre West Coast (Forschungs- und Technologiezentrum Westküste FTZ), | 3
Resiliense | 2
Ringkøbing-Skjern Kommune | 2
Robert Gordon University | 1
Rotterdam | 1
Royal College of Art | 1
Royal Haskoning DHV | 1
RUN | 1
RVO | 1
Safety Region - South Holland- Netherland | 5
Sala municipality | 4
Samn Forsyning | 4
Schleswig-Holstein Ministry for Energy Transition, Agriculture, Environment, Nature and Digitalization | 3
Schleswig-Holstein State Government – Germany | 5
Schønherr | 4
Schouwen Duiveland Council | 1
Scottish Environment Protection Agency | 1
Scottish Government | 1
Scottish Natural Heritage | 1
Seden Strandby Grundejerforening | 4
Sheffield AC | 2
Sheffield University | 1
Sielacht Dornum | 2
Sielacht Esens | 2
Simrishamns kommun, Sweden | 3
Skagen Uddannelsescenter | 1
Skånes vatten och avlopp, Sweden | 3
Skive Kommune | 4
Skurups kommun, Sweden | 3
Smagen af Danmark (Taste of Denmark) | 1
Smith Innovation | 4
Sogn og Fjordane fylkeskommune | 1
Solutionweb ApS | 1
Somerset Rivers Authority Project Manager Co-adapt | 2
South Norway European Office | 1
Southend on Sea Borough Council | 1
Southern Water- UK | 5
Stad Oostende (BE, Local authority) | 4
Ständige Vertretung der Bundesrepublik Deutchland bei der EU | 1
Stavanger region | 1
Stedin | 4
Stevns Kommune | 4
Stiftung Naturschutz | 1
Stockholm municipality | 4
Stockholm University, | 6
Strängnäs municipality | 4
Struer Kommune | 4
Sundbyberg municipality | 4
Svineholm Digelag (DNNK) | 4
Svinesundskommittén | 1
Sweco | 2
Sweden Water Research / WIN Water | 1
Swedish Agency for Economic and Regional Growth | 1
Swedish Agency Marine and Water Management | 3
Swedish Environmental Protection Agency, Sweden | 3
Swedish Geotechnical Institute | 2
Swedish Geotechnical Institute , Sweden | 3
Swedish Meteorological and Hydrological Institute | 2
Swedish National Road and Transport Research Institute - Sweden | 5
Swedish Transport Administration | 2
Syddjurs Kommune | 4
Syndicat Mixte baie de Somme - Grand Littoral Picard | 1
TEAM (Jacobs) | 2
Team2100 | 2
Tees Rivers Trust - UK | 5
Teknologiens Mediehus/Ingeniøren | 4
Teknologirådet | 4
Telemark | 1
Terra Nordica | 1
The Rivers Trust | 1
The Swedish Civil Contingencies Agency | 3
Thisted Kommune | 4
Tillväxtverkety | 1
Torsby municipality | 3
Trafikkontoret, Göteborgs stad - Sweden | 5
Transitions Research India | 6
Trelleborgs kommun, Sweden | 3
Trøndelag County Council | 1
TUHH Institute of River and Coastal Engineering | 1
Turnhout | 1
Tweed Forum | 1
UCL Erhvervsakademi og Professionshøjskole | 4
Umeå University | 2
UNESCO IHE | 1
Univ. Aalborg | 2
Univ. Copenhagen | 2
Univ. Delft | 2
Univ. Lund | 2
Univ. Utrecht | 2
Universidade de Aveiro | 2
Universidade de Coimbra | 2
Universidade de Trás-os-Monte e Alto Douro | 2
University of Antwerp, | 6
University of Canberra, | 6
University of Dundee | 1
University of Exeter | 2
University of Glasgow | 1
University of Hull | 1
University of Lund, Sweden | 3
University of Murcia | 6
University of Oldenburg | 1
Upplandsväsby municipality | 4
Uppsala municipality | 4
US Army Corps of Engineers | 1
US FHWA | 1
Valuing Water Initiative - Netherland | 5
Van Hall Larenstein | 1
Vandvender | 4
VanOs | 1
Västerås municipality | 4
Västra Götaland | 1
Veiligheidsregio | 4
Vejle | 2
Vejle kommune | 1
Vellinge kommun, Sweden | 3
Vest Agder | 1
Vestfold | 1
VGR | 1
VIA University College | 4
Videum AB | 1
Visit Värmland | 3
VIVES University College | 1
VLAIO | 1
Vordingborg Port | 1
Vrije University Brussels | 4
Washington State Department of Transport | 1
Water Alliance | 1
Waterschap Drents Overijsselse Delta | 4
Waterschap Hollandse Delta- Netherland | 5
Waterschap Scheldestromen (NL, Sectoral agency) | 4
waterschap Vechtstromen | 1
Wear Rivers Trust | 1
West 8 Landscape Architects - Netherland | 5
Westcountry Rivers Trust | 2
Westerkwartier Council | 1
Wetlands International | 1
World Maritime University, Sweden | 3
WSP | 4
Wulfsberg.dk | 4
Ystad kommun, Sweden | 3
YWPDK | 4
Additional, but without evidence because C5a did not host these events:
Report 3: the Dordrecht case was presented in a session at the Joint International Resilience Conference. 21 participants joined this session. Joint International Resilience Conference 2020 - Welcome (aanmelder.nl)
Report 4: Kystdirektoratet presented C5a as a part of a webmeeting in a national netwok, with 25 participants.
Report 5: Sayers presented C5a at the Next Level conference 2021. Estimated people that were reached: 200. NEXT LEVEL 2021 – Together we can build more resilient and liveable cities (20-10-2021). C5a was also presented at the COP26, with an estimation of 100 people reachted. HOME - UN Climate Change Conference (COP26) at the SEC – Glasgow 2021 (ukcop26.org) (31-10-2021 - 12-11-2021).
Report 6: Sayers presented C5a at the hybrid meeting of Outreach to China "Adaptation to Climate Change and Climate Resilience", with a conservative estimate of 25 participants.
Report 6: UT presented C5a at the Earth System Governance Bratislava Conference (8-9-2021).
Report 6: Varmland Encore conference 23-24 September 2021. Encore 2021 | Tullamore Ireland 2021 Conservative estimation of participants 100
Report 7:
The Varmland case studie was published in the newsletter of the Swedish Meteorological and Hydrological institute (SMHI), which has 1400 subscribers. As some of these subscribers maybe double from the list, 75% is taken from this total = 1050.
Report 7: Region Midjylland and Kystdirektoratet presented C5a at the National conference on cliamte adaptation 2019, Climate meeting Middelfart 2021 and Peoples festival of nature. Estimated informed particioants: 100. As these may not all be individual organisations, 75% of this number = 75
Report 7: the Flemish ambassador Griet Verstraeten informed 25 people about the C5a project. As these may not all be individual organisations, 75% of this number = 18
Report 7: Sayers included the C2C approach in training courses. Estimated outreach 500 people. As these may not all be individual organisations, 75% of this number = 375